C3M Project Activities and Timetable

## Phase				Activities				 Time Frame				Lead Team Members

| Phase 1 – The Team | • Work with LHS Tech Support to download Cmap Tools • Provide summary of concept mapping research and introductory materials to Gimble and Newkirk • Draft Cmap Tools Manual for LHS Educators • Meetings (2 days) to: - Introduce Cmap Tools - Collaborate on evaluation design - Develop strategy for Fall Classroom applications | July-August 2006 July-August 2006 July-August 2006 July-August 2006 | Jane Heinze-Fry Jane Heinze-Fry Jane Heinze-Fry, Barbara Newkirk, Elliott Gimble Jane Heinze-Fry, Barbara Newkirk, Elliott Gimble |
| --- | --- | --- | --- |
| Phase 2 – The Students | • Pre-unit Planning Meetings (2) • Develop first unit concept map • Develop second unit concept map • Implementation/Class Visits (2) • Evaluation/Next Steps Meetings (2) | September 2006/January 2007 September 2006 January 2007 October, 2006/February 2007 October, 2006/February 2007 | Jane Heinze-Fry, Barbara Newkirk, Elliott Gimble Jane Heinze-Fry B. Newkirk, E. Gimble Jane Heinze-Fry; Barbara Newkirk, Elliott Gimble Jane Heinze-Fry, |
| Phase 3 – The Report | • Consolidate and analyze data, draw conclusions, revise (as necessary) Manual, write final report | February – April, 2007 | Jane Heinze-Fry |
| Phase 4 – The Sharing | • Plan and implement 2-hour teacher training | April – May, 2007 | B. Newkirk, E. Gimble |