## Project Management
Project Management |  |  | OCT | NOV | DEC | JAN | FEB | MAR | APR | May | JUN
MMG Summit
Set Dates | bar: OCT
Reserve School Spaces (Small Gym, Auditorium, LGI, Physics, classrooms) | bar: OCT
Contact Partners | bar: JAN
Student projects | bar: OCT to APR
Campus wide projects
Partner booths
Chili Cook off
Publicity (VA and WVU) |  | (Write press release) | bar: FEB to APR
Panel Discussion
Surveys (Write and copy) | bar: FEB to APR
LCIC | (Send rep to oversight committee with updates) | bar: OCT to JUN
Thank yous | bar: May
Surveys Summaries | bar: JUN
Final Reports | bar: JUN

## Aimee
Aimee
Set up meetings with all groups
HSTA
WET
Band
Art
Create schedule for all locations with times
Beefie with 40 tables from the fairgrounds
Contact Drama for tech support for fashion show
Andrew Burress to help with computers at the Summit (Tech support)
Reserve 30 computers with Ms. Bass
Tickets for fashion show
Schedule for science classes of events

## Stu proj
Student Projects
Batteries
6th period
Chili Cook off
Tashana
Bird houses--Audubon
JT
Solar cars
White out
Concep
Kyle: Marching Band

## WET
WET
Danielle Amistadi
Room Assignments
Borrow camera and GPS from Brenda; charge batteries….
Publicity
Service Hours
Campus Projects
Tree planting |  | Schedule | (Photos!!)
Campus Clean up |  |  | (Photos!!)
Shed built |  |  | (Wear t-shirts)
Photographer
BLOG
Booth
Slide show
Pix of members
Backboard?
Mill Creek

## HSTA
HSTA
Stores
Bre | Goodwill
Clothing class
Jarohn with music
Models
Publicity
Student tickets for show

## ART
ART
Jen
Ecolab grant
Print project
Art Club
Rain barrel project
Contest?

## Band
BAND

## WVU
WVU
Panel Discussion

## Cacapon
Cacapon
Frank Rogers

## TMI
Brenda
TMI
Trouts Unlimited

## Herb
Herb
Forestry
Tree plan on property
Tags
Robert and Dale to take pictures
Tree list

## DEP
Ginny and Alana
DETP

## Trouts
Gary Berti
Trouts Unlimited
Tree Planting

## EPCD
Sara
EPCD

## Lowes
Lowes
Jamie Brown

## Opequon
Opequon
Gary Sylvester
Rain Barrels