## Project Management
Time-line: Project Management
Making Musselman Great | 2010-2011
| June | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | April | May
TASK
Program Overview
Goals | X | bar: Aug to Sept
Evaluation | X | bar: Aug to Sept
Assessment | X | bar: Aug to Sept
Oversight Committee | X | bar: Aug to Sept
Interim Report | X
Final Report | bar: May
Environmental Study | X | bar: Aug to April
Order Equipment | bar: Aug to Sept
Test and Assemble Equipment | bar: Aug to Sept
Survey Test Sites | bar: Aug to Sept
Schedule data collection | bar: Aug to Oct
Report Data | bar: Oct to April
Create biotic and abiotic inventories | bar: Oct to April
Data analysis | bar: Mar to May
Recommendations for future study | X
Training Sessions | bar: Aug to Sept
Contact Science Coordinator | bar: Aug to Sept
Schedule training sessions on-site | bar: Aug to Sept
Schedule training sessions off-site | bar: Aug to Sept
Environmental Seminars | bar: Aug; Nov; Feb
Classroom training sessions | bar: Sept to Nov
Fieldtrips and Field Studies | bar: Oct to Mar
Wetlands and Watershed Trips | bar: Oct to Nov; Mar to April
Stream Study | bar: Oct to Nov; Mar to April
Information Technology | bar: Aug
Set Goals | bar: Aug
Order Equipment | bar: Aug
Data Analysis | bar: Dec to Mar
Classroom Integration | bar: Aug to Mar
Implement Curriculum | bar: Oct to Nov
Select materials | bar: Aug to Sept
Teacher training | bar: Aug to Oct
Student training | bar: Sept to Oct
Student Mini-grants
Program Assessment
CSO Review | bar: Aug
Feedback and recommendations | bar: Aug to April
Final Report | bar: May

## Budget
Budget | Making Musselman Great
Total | 10000
Equipment |  |  |  | Vendor | Quantity |  | Price
White out |  |  |  | Lowes | 100 | 35 | 3500
Student research materials |  |  |  | Walmart | 25 | 24 | 600
Water Quality
| Stream Assay | (Lamotte water quality test kits) |  |  | 2 | 400 | 800
| Tree planting |  |  |  | 25 | 10 | 250
| Bus fees |  |  |  | 3 | 100 | 300
| Ice cube trays and buckets | [5 empty] | 20
Bird Houses |  | Carolina |  |  | 50 | 12 | 600
Landscaping: trees and plant materials |  |  | Trees | Allegheny nursery plants | 50 | 25 | 1250
|  |  | Plants |  |  |  | 150
|  | Wire cages, tubes, stakes, mulch |  |  |  |  | 250
Rain Barrels |  |  |  | Opequon | 12 | 65 | 780
| Paint |  |  | Lowes |  |  | 300
Band Instruments |  |  |  | G&M (used instruments) |  |  | 1200
10000
Note: Student research materials are specific to student projects and may vary.
Students must submit a plan; the grant coordinator will then review and purchase all materials.

## Project Timetable
Making Musselman Great Plans
Year Long Service
Blue bird and bat house outreach
Enviroscape Watershed training
White out roofs
Stream Assays
Stream tree planting
School tree planting
Rain garden
Rain barrels
Watershed test kits loans
Semester Service
Campus Clean-up
Education and Outreach
Water or Soil Testing
Bird and Bat education
Enviroscape Education
Tree planting
Green roof management
GPS or GIS assessment
Summit particpation
E-waste initiative
Biodiesel Demonstration