HIPs Action Plan Timeline

- Draft outline for Faculty Day workshop by June 22, 2012

- Develop Talking Points and Questions for VPs June 22

- Setting up appointments with

  - Melissa and Mel for week of June 25th (Participate, help inform students of HIPs)

  - Curt for week of July 9th

  - John for week of July 9th

  - Mary for week of June 25th

- Finalize workshop plan by July 27

- Prepare materials for workshop by July 27

  - LEAP handout with HIPs and questions on back

- List current practices with courses and activities that may be related

- Perhaps list on laptop and flip chart (Mary and Charro)

  - HIPs demo activity – come up with prompt for social survey

  - Menu of variety of sample HIP activities learned at conference

- Collect from team members

- Compile and publish faculty/student affairs HIPs activity lists by September 7

- By September 28 have a follow-up meeting with Provost and Student Affairs

- By September 28, review Key Characteristics by midterm for connections with HIPs (CILT with others)

- By September 28, schedule follow-up sessions around mid-term for faculty discussion and work

- By October 15, share compilation with Undergraduate Curriculum Committee and encourage discussion of connections and possible connections in the curriculum. Begin to look for potential sequencing and scaffolding opportunities.

- By October 15, share progress with Faculty Professional Development Committee for follow-up in plan for January Faculty Day.

- By December 7 have follow-up meeting with Undergraduate Curriculum Committee.

- By May 2013, update compiled list of activities based on Annual Faculty Activity Reports